## FR's
ID | Story Title | Depends On | Points | Priority | As a/an [user type] | I want [functionality] | So that [value] | Definition of Done | Epic ID | Status
S1 | Register |  | 2 | High | User | to be able to register an account on the website | So that I can recieve alerts later on about availabilty of facilities | I have an account on the website |  | Open
S2 | Login | S1 | 1 | High | User | to be able to login to my account on the website | So that I can access my saved data | I can see the alerts I set up |  | Open
S3 | Logout | S2 | 1 | High | User | to be able to logout of my account on the website | So that only I have access to my account | Shows home Screen/asking to login |  | Open
S4 | Search for Facilities |  | 8 | High | User | to be able to see all assisted living facilities in Maryland | So that I can decide which one is best for me | Displays assisted living facility information |  | Open
S5 | Facility Filters | S4 | 3 | Medium | User | to be able to filter living facilities by what they offer | So that I can pick the one that fits my needs | Displays specific living facilities based on requirements |  | Open
S6 | Location Filters | S4 | 3 | Medium | User | to be able to filter through living facilities based on location | So that I can pick the one that is in the area of my desire | Displays living facilities only in a specified area |  | Open
S7 | Information for Facility | S4 | 3 | Medium | User | to be able to see all information about a facility I click on | So that I can pick the one the facility thats best for me | Displays all information about living facility |  | Open
S8 | Notifications |  | 8 | Medium | User | to be able to receive a notification when there is a change in availability in a facility | So that I can see if a facility opened up | Recieve notification for facility |  | Open
S9 | Notification Preferences | S8 | 1 | Low | User | to be able to choose how to receive message notifications | So that I can receive alerts via email, text message, or both | Receive notifications through my chosen method |  | Open
S10 | Facility Listings |  | 8 | High | Admin | to be able to add/delete facilities and update any information | So that I can create new listings and keep information up to date | When im able to both create and manage facilities |  | Open
S11 | Upload Image for Facility | S10 | 1 | Medium | Admin | to be able to upload image of facility | so that users can see what it looks like | I can see my image near the listing |  | Open
S12 | Update Facility Images | S11 | 2 | Medium | Admin | to be able to change the image for a facility | so that facilities can make updates to their images for any changes | I can update the image for the listing |  | Open
S13 | Reset Password | S1 | 1 | Medium | User | to be able to reset my password | so that if i forget it, i can get back into my account | when Im able to reset my password |  | Open
S14 | Google Maps API |  | 2 | Medium | User | to be able to see where a facility is located on a map | so that I can see if its close by | when im able to see it on a map |  | Open
S15 | Contact Admin |  | 2 | Medium | User | to be able to create a message to contact admin | so that they can answer my question | My question is submitted to admins |  | Open
S16 | Read User Message | S15 | 2 | Medium | Admin | to be able to read Users messages | so that I can help answer their questions | I can see users questions |  | Open
S17 | Delete | S15 | 2 | Medium | Admin | to be able to delete Users messages | so that I can clean up my inbox | I can delete their message |  | Open
S18 | FAQ |  | 2 | Medium | User | to be able to see FAQ | so that maybe my question can be answered | When im able to see FAQ |  | Open
S19 | Saved Facilities |  | 2 | Low | User | to be able to save a posting for a facility | so that I can keep it stored for future reference | I can access the list of facilities that I have saved |  | Open
S20 | Remove Saved Facility | S19 | 1 | Low | User | to be able to remove a posting from my saved facilities | so that I can remove it from my list and not see it when I don't need it | The facility that I want to remove is no longer on the list |  | Open
S21 | Recently Viewed | S19 | 2 | Low | User | to be able to have a saved list of recently viewed facilities | so that I can go back to previous facilities I may like | The facilities that I've viewed recently are listed |  | Open
S22 | Pictures | S4 | 1 | High | User | to be able to see a picture of the facility | so that I can see if the facility is nice | When im able to see a picture of the facility |  | Open
S23 | Directions | S14 | 1 | High | User | to be able to have directions to any of the assisted living facilities | so that I can see how far the drive is | When im able to have directions to a facility |  | Open
S24 | Contact Information | S10 | 1 | High | User | to be able to have access to email and phone number of facility | so that i can contact the correct people if I have more questions | When im able to call/email the facility |  | Open
S25 | Comparing Facilities | S6 | 1 | Low | User | to be able to view the information of mulitple facilities at the same time | so that I can compare them between each other | When I can see multiple facilities simultaneously |  | Open
S26 | Featured Facilities | S4 | 1 | Low | User | to be able to view the most popular facilities | so that I can see which facilities are popular among everybody else | When I can view a list of featured facilities on the website |  | Open
S27 | Writing Reviews |  | 2 | Low | User | to be able to write a review for a facility | so that I can share my opinion for other users to use for reference | When I can create a review for a specific facility |  | Open
S28 | Deleting Reviews | S27 | 1 | Low | User | To be able to delete a review I made for a facility | so that I can remove a review in case I no longer want it posted | When I can delete my own review for a facility |  | Open
S29 | Reading Reviews | S27 | 1 | Low | User | To be able to view reviews for a facility | So that I can judge how good a facility is based on others experience | When I can see other reviews for a facility |  | Open
S30 | Realtime Updates | S8 | 2 | High | Admin | to be able to update the information of facilities in realtime | so that users can see the most up-to-date information available | When I make an update to a posting and users can immediately see it |  | Open
S31 | Walkthrough |  | 2 | Low | User | to be able to have a guided walkthrough of the website | so that I can understand the layout of the website | When I am able to access a guided walkthrough of the website |  | Open
S32 | Profile Management | S1 | 5 | High | User | to be able to manage my account | So that I can view it, make updated changes, and delete it | When I am able to edit my own personal account and also delete it |  | Open
S33 | Insurance Filters | S4 | 3 | Medium | User | to be able to filter facilities based on my insurance coverage | So that I can find facilities that are compatible with my insurance | When facilities shown are only those compatible with my insurance |  | Open
S34 | Sorting | S4 | 2 | Medium | User | to be able to sort my searches based on price, proximity, etc. | So that I can compare and contrast my filtered facilities | When filtered facilities being searched for are sorted properly |  | Open

## NFR's
The [system name] | shall have [instance] | with this [feature]
The website | shall have the same design and layout as the client's website | with this design
The images | shall all be uploaded in JPEG format and not PNG | with this performance